## Sheet1
Uge | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Recieve equipment. | Recieve equipment.
| understand equipment in regards to usage | understand equipment in regards to usage
| Test equipment | Test equipment
| Document equipment | Document equipment
Make test setup where we can transmit and recieve some signal with internal modulation and display osciliscope
API til waveform generator. Implement necessary commands.Or find API that already can do this.
Audio conversion to array
Send the value 42
få mathias kniv ide til at virke:)
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Transmitter side: - RS-232 cable to connect input source to: - Fucntion/Wave generator - Underwater Speaker (Using BNC adapter) Receiver side: - hydrophone - loging device - oscilloscope or sound card - maybe an amplifier
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Transmitter side: - RS-232 cable to connect input source to: - Fucntion/Wave generator - Underwater Speaker (Using BNC adapter) Receiver side: - hydrophone - loging device - oscilloscope or sound card - maybe an amplifier